## Pre-Re-homing Activities
2020-03-19
PRE-RE-HOMING ACTIVITIES
Software Packages
Activity | Name
Delete | POSS13
Create | PREREHOM
Command Calendar Task
1
2
3
4
5
!*******************************************************!
!*** Pre-Re-homing Activities - Alvaro R. Mendoza ******!
!*** Date: 2020-3-19 ***********************************!
!*******************************************************!
## !****************************************! ##
## Step // BLOCK COMMAND CALENDAR //
ZICL;
ZICB:1:BLOCK;
ZICB:2:BLOCK;
ZICB:3:BLOCK;
ZICB:4:BLOCK;
ZICB:5:BLOCK;
ZICL;
## Step // BACKUP //
## Step / DELETE OLD PACKAGE /
ZWQO:CR;
ZWQD:NAME=POSS13:DIRE,PRINTS;
ZWQO:CR;
## Step / CREATE FALLBACK /
ZWQO:CR;
ZWKS:NAME=PREREHOM,DIRE=PREREHOM,MODE=FULL;
ZWQO:CR;
## Step / PRINT PROGRESS OF FALLBACK /
ZWKI;
@Stop
## Step / CHECK THE STATUS OF FALLBACK (PHASES AND FILES WHERE HAS OCCURED ERROR) /
ZWKP:FULL:EMODE;
## Step / CHECK THE STATUS OF FALLBACK (ALL PHASES AND FILES) /
ZWKP:FULL:TOTAL;
## Step / VERIFY THE FALLBACK PACKAGE /
ZWQB:NAME=PREREHOM:FORM=FAILED,CW=ALL;
## Step // COPY NEWEST & VERIFIED FALLBACK TO FO //
## Step / VERIFY FREE SPACE ON MAGNETO-OPTICAL DISK /
ZIWX::F0,NODEF::%,%;
## Step / COPY THE BUILD FROM DISK TO MAGNETO-OPTICAL DISK /
ZIWY:S:DRIVE=WDU-B,PATH=/PREREHOM/;
ZIWY:D:DRIVE=FDU-N0,PATH=/,DRIVE=FDU-N0;
ZIBC:,,,,,,,,,DIR:DSN=PREREHOM;
## Step / VERIFY FREE SPACE ON MAGNETO-OPTICAL DISK /
ZIWX::F0,NODEF::%,%;
## !****************************************! ##

## Re-homing BSC 1° Case
43909
REHOMING BSC FROM ONE MGW TO ANOTHER WITH SAME MSS
Yes
No
Original Signaling |  |  | Hex/Dec Calculator
SPC Name | SPC (Dec) | SPC (Hexa) | From Hex to Dec
BBA35 | 16348 | 3FDC | 3FEA | 16362
MGBA2 | 16334 | 3FCE | From Dec to Hex
MVBAA | 14321 | 37F1 | 16344 | 3FD8 | 2020-03-19
↓
Newest Signaling
SPC Name | SPC (Dec) | SPC (Hexa)
BBA35 | 16348 | 3FDC
MGBA6 | 16376 | 3FF8
MVBAA | 14321 | 37F1
Signalling Links to rehoming
|  | 0 |  |  | 1
|  | 1 |  |  | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
| Last Link | 1 |  |  | 0
!**********************************************************************************!
!*** Re-homing BSC from one MGW to another with same MSS - Alvaro R. Mendoza ******!
!*** Date: 2020-3-19 **************************************************************!
!**********************************************************************************!
! ORIGINAL SIGNALING PARAMETERS
! BBA35 16348 3FDC
! MGBA2 16334 3FCE
! MVBAA 14321 37F1
! NEWEST SIGNALING PARAMETERS
! BBA35 16348 3FDC
! MGBA6 16376 3FF8
! MVBAA 14321 37F1
## !****************************************! ##
## Step // BLOCK SIGNALLING //
## Step / CHANGE 1° SIGNALLING LINK STATE /
ZNLI;
ZNLC:0,INA;
ZNLI;
!@Stop
## Step / DENY ACTIVATION OF 1° SIGNALLING LINKS /
ZNEL;
ZNLD:0;
ZNEL;
!@Stop
## Step // HARDWARE RE-HOMING - (1° JUMPER EXCHANGE) //
## Step // RE-HOMING //
## Step / DELETE 1° SIGNALING LINK FROM OLD LINK SET /
ZNSI:NA1;
ZNSR:NA1,3FCE,MGBA2:0;
ZNSI:NA1;
!@Stop
## Step / CREATE SIGNALING LINK SET (TO NEW MGW) /
ZNSI:NA1;
ZNSC:NA1,3FF8,MGBA6:0,0;
ZNSI:NA1;
!@Stop
## Step / CREATE SIGNALLING ROUTE SET (TO NEW MGW) /
ZNRI:NA1;
ZNRC:NA1,3FF8,MGBA6,1,,N:NA1,3FF8,MGBA6,0;
ZNRI:NA1;
!@Stop
## Step / ADD SIGNALLING ROUTE TO ROUTE SET /
ZNRI:NA1;
ZNRA:NA1,37F1,MVBAA:NA1,3FF8,MGBA6,0:;
ZNRI:NA1;
## Step / ALLOW ACTIVATION OF 1° SIGNALLING LINKS /
ZNLI;
ZNLA:0;
ZNLI;
!@Stop
## Step / CHANGE 1° SIGNALLING LINK STATE /
ZNLI;
ZNLC:0,ACT;
ZNLI;
!@Stop
## Step / CHANGE SCCP STATE /
ZNGI:NA1;
ZNGC:NA1,3FDC:ACT;
ZNGC:NA1,3FF8:ACT;
ZNGC:NA1,37F1:ACT;
ZNGI:NA1;
!@Stop
## Step / CHANGE SUBSYSTEM STATE /
ZNHI:NA1;
ZNHC:NA1,3FDC:FE:ACT;
ZNHC:NA1,37F1:FE:ACT;
ZNHI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVA:NA1,3FF8;
ZNVA:NA1,37F1:NA1,3FF8;
ZNVA:NA1,3FF8:NA1,3FF8;
ZNVI:NA1;
!@Stop
## Step / CHANGE ROUTE SET STATE /
ZNVI:NA1;
ZNVC:NA1,3FF8::ACT;
ZNVC:NA1,37F1:NA1,3FF8:ACT;
ZNVI:NA1;
!@Stop
!!!!!!!!!!!!!!!!!!!!!!! If everything is right !!!!!!!!!!!!!!!!!!!!!!!
## Step // HARDWARE RE-HOMING - (JUMPER EXCHANGE - ALL OTHER ONES) //
## Step // BLOCK SIGNALLING //
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:1,INA;
ZNLC:1,INA;
ZNLI;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING LINKS /
ZNEL;
ZNLD:1;
ZNLD:1;
ZNEL;
!@Stop
## Step / DELETE SIGNALING LINK FROM OLD LINK SET /
ZNSI:NA1;
ZNSR:NA1,3FCE,MGBA2:1;
ZNSI:NA1;
!@Stop
## Step / CHANGE SIGNALLING ROUTE STATE /
ZNVI:NA1;
ZNVC:NA1,3FCE:NA1,3FCE:INA;
ZNVC:NA1,37F1:NA1,3FCE:INA;
ZNVI:NA1;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVD:NA1,3FCE;
ZNVD:NA1,3FCE:NA1,3FCE;
ZNVD:NA1,37F1:NA1,3FCE;
ZNVI:NA1;
!@Stop
## Step / DELETE SIGNALLING ROUTE FROM ROUTE SET /
ZNRI:NA1;
ZNRR:NA1,37F1,MVBAA:NA1,3FCE,MGBA2;
ZNRI:NA1;
## Step / DELETE SIGNALLING ROUTE SET /
ZNRI:NA1;
ZNRD:NA1,3FCE,MGBA2;
ZNRI:NA1;
## Step / DELETE SIGNALLING LINK SET /
ZNSI:NA1;
ZNSD:NA1,3FCE,MGBA2;
ZNSI:NA1;
## Step / ADD SIGNALLING LINK TO LINK SET (TO NEW MGW) /
ZNSI:NA1;
ZNSA:NA1,3FF8,MGBA6:1,1;
ZNSA:NA1,3FF8,MGBA6:1,1;
ZNSI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING LINKS /
ZNLI;
ZNLA:1;
ZNLA:1;
ZNLI;
!@Stop
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:1,ACT;
ZNLC:1,ACT;
ZNLI;
!@Stop
## Step / CHANGE SCCP STATE /
ZNGI:NA1;
ZNGC:NA1,3FDC:ACT;
ZNGC:NA1,3FF8:ACT;
ZNGC:NA1,37F1:ACT;
ZNGI:NA1;
!@Stop
## Step / CHANGE SUBSYSTEM STATE /
ZNHI:NA1;
ZNHC:NA1,3FDC:FE:ACT;
ZNHC:NA1,37F1:FE:ACT;
ZNHI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVA:NA1,3FF8;
ZNVA:NA1,3FF8:NA1,3FF8;
ZNVA:NA1,37F1:NA1,3FF8;
ZNVI:NA1;
!@Stop
## Step / CHANGE ROUTE SET STATE /
ZNVI:NA1;
ZNVC:NA1,3FF8::ACT;
ZNVC:NA1,37F1:NA1,3FF8:ACT;
ZNVI:NA1;
!@Stop
## !****************************************! ##
## Step // RESET BSC //
!ZUSS:SYM:C=DSK;
## Step // VERIFY CONFIGURATIONS //
## Step / VERIFY SIGNALLING BSC/MGW/MSS /
ZNET;
ZNEL;
ZNCI;
ZNLI;
ZNET:NA1;
ZNEO:NA1;
ZNES:NA1;
ZNER:NA1;
ZNRI:NA1;
ZNRT::NA1;
ZNSI:NA1;
ZNFJ:NA1;
ZNFI:NA1;
ZNVI:NA1;
ZNGI:NA1;
ZNHI:NA1;
ZNHJ:NA1;
ZNPI:NA1;
ZOBI:NA1;
ZOBL:NA1;
## !****************************************! ##

## Re-homing BSC 2° Case
43909
REHOMING BSC FROM TWO MGW TO ONE MGW WITH SAME MSS
Yes
No
Original Signaling |  |  |  | Original Signaling |  |  | Hex/Dec Calculator
SPC Name | SPC (Dec) | SPC (Hexa) |  | SPC Name | SPC (Dec) | SPC (Hexa) | From Hex to Dec
BDF32 | 16343 | 3FD7 |  | BDF32 | 16343 | 3FD7 | 3FF8 | 16376
MGDF2 | 16335 | 3FCF |  | MGDF1 | 16334 | 3FCE | From Dec to Hex
MSDF1 | 7905 | 1EE1 |  | MSDF1 | 7905 | 1EE1 | 16344 | 3FD8 | 2020-03-19
↓ |  |  | ↙
Newest Signaling
SPC Name | SPC (Dec) | SPC (Hexa)
BDF32 | 16343 | 3FD7
MGDF2 | 16335 | 3FCF
MSDF1 | 7905 | 1EE1
Signalling Links to rehoming
|  | 0 | [6 empty] | 1
|  | 1 | [6 empty] | 0
|  | 2 | [6 empty] | 0
|  | 3 | [6 empty] | 0
|  | 4 | [6 empty] | 0
|  | 5 | [6 empty] | 0
|  | 6 | [6 empty] | 0
| Last Link | 7 | [6 empty] | 0
!**********************************************************************************!
!*** Re-homing BSC from two MGW to one MGW with same MSS - Alvaro R. Mendoza ******!
!*** Date: 2020-3-19 **************************************************************!
!**********************************************************************************!
! ORIGINAL SIGNALING PARAMETERS GOING VIA 1° MGW
! BDF32 16343 3FD7
! MGDF2 16335 3FCF
! MSDF1 7905 1EE1
! ORIGINAL SIGNALING PARAMETERS GOING VIA 2° MGW
! BDF32 16343 3FD7
! MGDF1 16334 3FCE
! MSDF1 7905 1EE1
! NEWEST SIGNALING PARAMETERS (BSC ONLY VIA 1° MGW)
! BDF32 16343 3FD7
! MGDF2 16335 3FCF
! MSDF1 7905 1EE1
## !****************************************! ##
## Step // BLOCK SIGNALLING //
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:0,INA;
ZNLC:1,INA;
ZNLC:2,INA;
ZNLC:3,INA;
ZNLC:4,INA;
ZNLC:5,INA;
ZNLC:6,INA;
ZNLC:7,INA;
ZNLI;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING LINKS /
ZNEL;
ZNLD:0;
ZNLD:1;
ZNLD:2;
ZNLD:3;
ZNLD:4;
ZNLD:5;
ZNLD:6;
ZNLD:7;
ZNEL;
!@Stop
## Step // HARDWARE RE-HOMING - (JUMPER EXCHANGE) //
## Step // RE-HOMING //
## Step / DELETE SIGNALING LINK FROM OLD LINK SET /
ZNSI:NA1;
ZNSR:NA1,MGDF1,3FCE:0;
ZNSR:NA1,MGDF1,3FCE:1;
ZNSR:NA1,MGDF1,3FCE:2;
ZNSR:NA1,MGDF1,3FCE:3;
ZNSR:NA1,MGDF1,3FCE:4;
ZNSR:NA1,MGDF1,3FCE:5;
ZNSR:NA1,MGDF1,3FCE:6;
!ZNSR:NA1,MGDF1,3FCE:7;
ZNSI:NA1;
!@Stop
## Step / ADD SIGNALING LINK TO LINK SET (TO NEW MGW) /
ZNSI:NA1;
ZNSA:NA1,3FCF,MGDF2:0,8;
ZNSA:NA1,3FCF,MGDF2:1,9;
ZNSA:NA1,3FCF,MGDF2:2,10;
ZNSA:NA1,3FCF,MGDF2:3,11;
ZNSA:NA1,3FCF,MGDF2:4,12;
ZNSA:NA1,3FCF,MGDF2:5,13;
ZNSA:NA1,3FCF,MGDF2:6,14;
ZNSI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING LINKS /
ZNLI;
ZNLA:0;
ZNLA:1;
ZNLA:2;
ZNLA:3;
ZNLA:4;
ZNLA:5;
ZNLA:6;
ZNLI;
!@Stop
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:0,ACT;
ZNLC:1,ACT;
ZNLC:2,ACT;
ZNLC:3,ACT;
ZNLC:4,ACT;
ZNLC:5,ACT;
ZNLC:6,ACT;
ZNLI;
!@Stop
!!!!!!!!!!!!!!!!!!!!!!! If everything is right !!!!!!!!!!!!!!!!!!!!!!!
## Step // BLOCK SIGNALLING //
## Step / CHANGE SIGNALLING ROUTE STATE /
ZNVI:NA1;
ZNVC:NA1,3FCE:NA1,3FCE:INA;
ZNVC:NA1,1EE1:NA1,3FCE:INA;
ZNVI:NA1;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVD:NA1,3FCF;
ZNVD:NA1,3FCE:NA1,3FCE;
ZNVD:NA1,1EE1:NA1,3FCE;
ZNVI:NA1;
!@Stop
## Step / DELETE SIGNALLING ROUTE FROM ROUTE SET /
ZNRI:NA1;
ZNRR:NA1,1EE1,MSDF1:NA1,3FCE,MGDF1;
ZNRI:NA1;
## Step / DELETE SIGNALLING ROUTE SET /
ZNRI:NA1;
ZNRD:NA1,3FCE,MGDF1;
ZNRI:NA1;
## Step / DELETE SIGNALLING LINK SET /
ZNSI:NA1;
ZNSD:NA1,3FCE,MGDF1;
ZNSI:NA1;
## Step / ADD SIGNALLING LINK TO LINK SET (TO NEW MGW) /
ZNSI:NA1;
ZNSA:NA1,3FCF,MGDF2:7,15;
ZNSI:NA1;
## Step / ALLOW ACTIVATION OF SIGNALLING LINKS /
ZNLI;
ZNLA:7;
ZNLI;
!@Stop
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:7,ACT;
ZNLI;
## Step / CHANGE SCCP STATE /
ZNGI:NA1;
ZNGC:NA1,3FD7:ACT;
ZNGC:NA1,3FCF:ACT;
ZNGC:NA1,1EE1:ACT;
ZNGI:NA1;
!@Stop
## Step / CHANGE SUBSYSTEM STATE /
ZNHI:NA1;
ZNHC:NA1,3FD7:FE:ACT;
ZNHC:NA1,1EE1:FE:ACT;
ZNHI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVA:NA1,3FCF;
ZNVA:NA1,1EE1:NA1,3FCF;
ZNVA:NA1,3FCF:NA1,3FCF;
ZNVI:NA1;
!@Stop
## Step / CHANGE ROUTE SET STATE /
ZNVI:NA1;
ZNVC:NA1,3FCF::ACT;
ZNVC:NA1,1EE1:NA1,3FCF:ACT;
ZNVI:NA1;
!@Stop
## !****************************************! ##
## Step // RESET BSC //
!ZUSS:SYM:C=DSK;
## Step // VERIFY CONFIGURATIONS //
## Step / VERIFY SIGNALLING BSC/MGW/MSS /
ZNET;
ZNEL;
ZNCI;
ZNLI;
ZNET:NA1;
ZNEO:NA1;
ZNES:NA1;
ZNER:NA1;
ZNRI:NA1;
ZNRT::NA1;
ZNSI:NA1;
ZNFJ:NA1;
ZNFI:NA1;
ZNVI:NA1;
ZNGI:NA1;
ZNHI:NA1;
ZNHJ:NA1;
ZNPI:NA1;
ZOBI:NA1;
ZOBL:NA1;
## !****************************************! ##

## Re-homing BSC 3° Case
43909
REHOMING BSC FROM ONE MGW TO TWO MGW WITH SAME MSS
Yes
No
Original Signaling |  |  |  | Hex/Dec Calculator
SPC Name | SPC (Dec) | SPC (Hexa) |  | From Hex to Dec
BBA35 | 16348 | 3FDC |  | 3FF8 | 16376
MGB05 | 16344 | 3FD8 |  | From Dec to Hex
MVBA9 | 12497 | 30D1 |  | 16344 | 3FD8 |  | 2020-03-19
↓ |  |  | ↘
Newest Signaling |  |  |  | Newest Signaling
SPC Name | SPC (Dec) | SPC (Hexa) |  | SPC Name | SPC (Dec) | SPC (Hexa)
BBA35 | 16348 | 3FDC |  | BBA35 | 16348 | 3FDC
MGB05 | 16344 | 3FD8 |  | MGB14 | 15787 | 3DAB
MVBA9 | 12497 | 30D1 |  | MVBA9 | 12497 | 30D1
Signalling Links to rehoming
|  | 0 |  |  |  |  | 1
0
0
0
0
0
0
| Last Link | 1 |  |  |  |  | 0
!**********************************************************************************!
!*** Re-homing BSC from one MGW to two MGW with same MSS - Alvaro R. Mendoza ******!
!*** Date: 2020-3-19 **************************************************************!
!**********************************************************************************!
! ORIGINAL SIGNALING PARAMETERS (BSC ONLY VIA 1° MGW)
! BBA35 16348 3FDC
! MGB05 16344 3FD8
! MVBA9 12497 30D1
! NEWEST SIGNALING PARAMETERS (BSC VIA 1° MGW)
! BBA35 16348 3FDC
! MGB05 16344 3FD8
! MVBA9 12497 30D1
! NEWEST SIGNALING PARAMETERS (BSC VIA 2° MGW)
! BBA35 16348 3FDC
! MGB14 15787 3DAB
! MVBA9 12497 30D1
## !****************************************! ##
## Step // BLOCK SIGNALLING //
## Step / CHANGE 1° SIGNALLING LINK STATE /
ZNLI;
ZNLC:0,INA;
ZNLI;
!@Stop
## Step / DENY ACTIVATION OF 1° SIGNALLING LINKS /
ZNEL;
ZNLD:0;
ZNEL;
!@Stop
## Step // HARDWARE RE-HOMING - (1° JUMPER EXCHANGE) //
## Step // RE-HOMING //
## Step / DELETE 1° SIGNALING LINK FROM OLD LINK SET /
ZNSI:NA1;
ZNSR:NA1,MGB05,3FD8:0;
ZNSI:NA1;
!@Stop
## Step / CREATE SIGNALING LINK SET (TO NEW 2° MGW) /
ZNSI:NA1;
ZNSC:NA1,3DAB,MGB14:0,0;
ZNSI:NA1;
!@Stop
## Step / CREATE SIGNALLING ROUTE SET (TO NEW 2° MGW) /
ZNRI:NA1;
ZNRC:NA1,3DAB,MGB14,1,,N:NA1,3DAB,MGB14,0;
ZNRI:NA1;
!@Stop
## Step / ADD SIGNALLING ROUTE TO ROUTE SET /
ZNRI:NA1;
ZNRA:NA1,30D1,MVBA9:NA1,3DAB,MGB14,3FDC:;
ZNRI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF 1° SIGNALLING LINKS /
ZNLI;
ZNLA:0;
ZNLI;
!@Stop
## Step / CHANGE SCCP STATE /
ZNGI:NA1;
ZNGC:NA1,3FDC:ACT;
ZNGC:NA1,3FD8:ACT;
ZNGC:NA1,3DAB:ACT;
ZNGC:NA1,30D1:ACT;
ZNGI:NA1;
!@Stop
## Step / CHANGE SUBSYSTEM STATE /
ZNHI:NA1;
ZNHC:NA1,3FDC:FE:ACT;
ZNHC:NA1,30D1:FE:ACT;
ZNHI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVA:NA1,3FD8;
ZNVA:NA1,30D1:NA1,3FD8;
ZNVA:NA1,3FD8:NA1,3FD8;
ZNVA:NA1,3DAB;
ZNVA:NA1,30D1:NA1,3DAB;
ZNVA:NA1,3DAB:NA1,3DAB;
ZNVI:NA1;
!@Stop
## Step / CHANGE ROUTE SET STATE /
ZNVI:NA1;
ZNVC:NA1,3FD8::ACT;
ZNVC:NA1,30D1:NA1,3FD8:ACT;
ZNVC:NA1,3DAB::ACT;
ZNVC:NA1,30D1:NA1,3DAB:ACT;
ZNVI:NA1;
!@Stop
!!!!!!!!!!!!!!!!!!!!!!! If everything is right !!!!!!!!!!!!!!!!!!!!!!!
## Step // HARDWARE RE-HOMING - (JUMPER EXCHANGE - ALL OTHER ONES) //
## Step // BLOCK SIGNALLING //
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:1,INA;
ZNLI;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING LINKS /
ZNEL;
ZNLD:1;
ZNEL;
!@Stop
## Step / DELETE SIGNALING LINK FROM OLD LINK SET /
ZNSI:NA1;
ZNSR:NA1,3FD8,MGB05:FALSO;
ZNSR:NA1,3FD8,MGB05:FALSO;
ZNSR:NA1,3FD8,MGB05:FALSO;
ZNSR:NA1,3FD8,MGB05:FALSO;
ZNSR:NA1,3FD8,MGB05:FALSO;
ZNSR:NA1,3FD8,MGB05:FALSO;
ZNSR:NA1,3FD8,MGB05:1;
ZNSI:NA1;
!@Stop
## Step / ADD SIGNALING LINK TO LINK SET (TO NEW MGW) /
ZNSI:NA1;
ZNSA:NA1,3DAB,MGB14:FALSO,FALSO;
ZNSA:NA1,3DAB,MGB14:FALSO,FALSO;
ZNSA:NA1,3DAB,MGB14:FALSO,FALSO;
ZNSA:NA1,3DAB,MGB14:FALSO,FALSO;
ZNSA:NA1,3DAB,MGB14:FALSO,FALSO;
ZNSA:NA1,3DAB,MGB14:FALSO,FALSO;
ZNSA:NA1,3DAB,MGB14:1,1;
ZNSI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING LINKS /
ZNLI;
ZNLA:FALSO;
ZNLA:FALSO;
ZNLA:FALSO;
ZNLA:FALSO;
ZNLA:FALSO;
ZNLA:FALSO;
ZNLA:1;
ZNLI;
!@Stop
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:FALSO,ACT;
ZNLC:FALSO,ACT;
ZNLC:FALSO,ACT;
ZNLC:FALSO,ACT;
ZNLC:FALSO,ACT;
ZNLC:FALSO,ACT;
ZNLC:1,ACT;
ZNLI;
!@Stop
## Step / CHANGE SCCP STATE /
ZNGI:NA1;
ZNGC:NA1,3FDC:ACT;
ZNGC:NA1,3FD8:ACT;
ZNGC:NA1,3DAB:ACT;
ZNGC:NA1,30D1:ACT;
ZNGI:NA1;
!@Stop
## Step / CHANGE SUBSYSTEM STATE /
ZNHI:NA1;
ZNHC:NA1,3FDC:FE:ACT;
ZNHC:NA1,30D1:FE:ACT;
ZNHI:NA1;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVA:NA1,3FD8;
ZNVA:NA1,30D1:NA1,3FD8;
ZNVA:NA1,3FD8:NA1,3FD8;
ZNVA:NA1,3DAB;
ZNVA:NA1,30D1:NA1,3DAB;
ZNVA:NA1,30D1:NA1,30D1;
ZNVI:NA1;
!@Stop
## Step / CHANGE ROUTE SET STATE /
ZNVI:NA1;
ZNVC:NA1,3FD8::ACT;
ZNVC:NA1,30D1:NA1,3FD8:ACT;
ZNVC:NA1,3DAB::ACT;
ZNVC:NA1,30D1:NA1,3DAB:ACT;
ZNVI:NA1;
!@Stop
## !****************************************! ##
## Step // RESET BSC //
!ZUSS:SYM:C=DSK;
## Step // VERIFY CONFIGURATIONS //
## Step / VERIFY SIGNALLING BSC/MGW/MSS /
ZNET;
ZNEL;
ZNCI;
ZNLI;
ZNET:NA1;
ZNEO:NA1;
ZNES:NA1;
ZNER:NA1;
ZNRI:NA1;
ZNRT::NA1;
ZNSI:NA1;
ZNFJ:NA1;
ZNFI:NA1;
ZNVI:NA1;
ZNGI:NA1;
ZNHI:NA1;
ZNHJ:NA1;
ZNPI:NA1;
ZOBI:NA1;
ZOBL:NA1;
## !****************************************! ##

## Re-homing BSC 4° Case
43909
REHOMING BSC FROM ONE MGW/MSS TO ANOTHER MGW/MSS
Yes
No
Original Signaling |  |  | Hex/Dec Calculator
SPC Name | SPC (Dec) | SPC (Hexa) | From Hex to Dec
BSC28 | 15691 | 3D4B | 3FEA | 16362
MGW01 | 16334 | 3FCE | From Dec to Hex
MSS03 | 6492 | 195C | 16344 | 3FD8 | 2020-03-19
↓
Newest Signaling
SPC Name | SPC (Dec) | SPC (Hexa)
BSC28 | 15691 | 3D4B
MGW04 | 7310 | 1C8E
MSS06 | 16337 | 3FD1
Signalling Links to rehoming
|  | 0 |  |  | 1
|  | 1 |  |  | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
!**********************************************************************************!
!*** Re-homing BSC from one MGW/MSS to another MGW/MSS - Alvaro R. Mendoza ******!
!*** Date: 2020-3-19 **************************************************************!
!**********************************************************************************!
! ORIGINAL SIGNALING PARAMETERS
! BSC28 15691 3D4B
! MGW01 16334 3FCE
! MSS03 6492 195C
! NEWEST SIGNALING PARAMETERS
! BSC28 15691 3D4B
! MGW04 7310 1C8E
! MSS06 16337 3FD1
## !****************************************! ##
## !***** DELETE WHOLE SYSTEM'S SIGNALING **! ##
## Step // DELETE CIRCUITS GROUPS //
ZRCI:SEA=3:CGR=1&2&3:PRINT=5;
ZRCD:CGR=1;
ZRCD:CGR=2;
!ZRCD:CGR=3;
ZRCI:SEA=3:CGR=1&2&3:PRINT=5;
## Step / CHANGE SUBSYSTEM STATE /
ZNHI:NA1;
ZNHC:NA1,3D4B:FE:INA;
ZNHC:NA1,3FCE:FE:INA;
ZNHC:NA1,195C:FE:INA;
ZNHI:NA1;
!@Stop
## Step / CHANGE SCCP STATE /
ZNGI:NA1;
ZNGC:NA1,3D4B:INA:;
ZNGC:NA1,3FCE:INA:;
ZNGC:NA1,195C:INA:;
ZNGI:NA1;
!@Stop
## Step / MODIFY BROADCAST STATUS OF SCCP SIGNALLING POINTS /
ZOBI:NA1;
ZOBL:NA1;
ZOBM:NA1,3D4B,FE::N:;
ZOBM:NA1,3FCE,FE::N:;
ZOBM:NA1,195C,FE::N:;
ZOBC:NA1,3D4B,FE::N:;
ZOBC:NA1,3FCE,FE::N:;
ZOBC:NA1,195C,FE::N:;
ZOBI:NA1;
ZOBL:NA1;
!@Stop
## Step / CHANGE SIGNALLING ROUTE STATE /
ZNVI:NA1;
ZNVC:NA1,3FCE::INA;
ZNVC:NA1,195C:NA1,3FCE:INA;
ZNVI:NA1;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVD:NA1,3FCE::;
ZNVD:NA1,3FCE:NA1,3FCE:;
ZNVD:NA1,195C:NA1,3FCE:;
ZNVI:NA1;
!@Stop
## Step / CHANGE SIGNALLING LINK STATE /
ZNEL;
ZNLC:0,INA;
ZNLC:1,INA;
ZNEL;
!@Stop
## Step / DENY ACTIVATION OF SIGNALLING LINKS /
ZNEL;
ZNLD:0;
ZNLD:1;
ZNEL;
!@Stop
## Step / REMOVE SCCP FROM SIGNALLING POINTS /
ZNFI:NA1;
ZNFR:NA1,195C:;
ZNFR:NA1,3D4B:;
ZNFI:NA1;
!@Stop
## Step / DELETE SERVICE /
ZNPI:NA1;
ZNPD:NA1,03,SCCP:;
ZNPI:NA1;
!@Stop
## Step / DELETE SIGNALLING ROUTE SET /
ZNRI:NA1;
ZNRD:NA1,195C,MSS03:;
ZNRD:NA1,3FCE,MGW01:;
ZNRI:NA1;
!@Stop
## Step / DELETE SIGNALLING LINK FROM LINK SET /
ZNSI:NA1;
ZNSR:NA1,3FCE,MGW01:1:;
ZNSI:NA1;
!@Stop
## Step / DELETE SIGNALLING LINK SET /
ZNSI:NA1;
ZNSD:NA1,3FCE,MGW01:;
ZNSI:NA1;
!@Stop
## !****************************************! ##
## !***** CREATE WHOLE SYSTEM'S SIGNALING **! ##
## Step // CREATE SIGNALLING LINK SET //
ZNRI:NA1;
ZNSI:NA1;
ZNSC:NA1,1C8E,MGW04:0,0;
ZNSA:NA1,1C8E,MGW04:1,1;
ZNSI:NA1;
!@Stop
## Step // CREATE SIGNALLING ROUTE SET //
ZNRI:NA1;
ZNRC:NA1,1C8E,MGW04,1,,N:,,,0;
ZNRC:NA1,3FD1,MSS06,1,,N:NA1,1C8E,MGW04,0;
ZNRI:NA1;
!@Stop
## Step // ALLOW ACTIVATION OF SIGNALLING LINKS //
ZNLI;
ZNLA:0;
ZNLA:1;
ZNLI;
!@Stop
## Step / ALLOW ACTIVATION OF SIGNALLING ROUTE /
ZNVI:NA1;
ZNVA:NA1,1C8E;
ZNVA:NA1,3FD1:NA1,1C8E;
ZNVI:NA1;
!@Stop
## Step / CHANGE SIGNALLING LINK STATE /
ZNLI;
ZNLC:0,ACT;
ZNLC:1,ACT;
ZNLI;
!@Stop
## Step / CHANGE ROUTE SET STATE /
ZNVI:NA1;
ZNVC:NA1,1C8E::ACT;
ZNVC:NA1,3FD1:NA1,1C8E:ACT;
ZNVI:NA1;
!@Stop
## Step // CREATE SCCP SERVICE //
ZNPI:NA1;
ZNPC:NA1,03,SCCP:Y:Y,,;
ZNPI:NA1;
!@Stop
## Step // DEFINE SCCP FOR SIGNALLING POINT //
ZNFI:NA1;
ZNFD:NA1,3D4B,1:FE,BSSAP,1,:::::;
ZNFD:NA1,3FD1,1:FE,BSSAP,1,:::::;
ZNFI:NA1;
!@Stop
## Step // MODIFY BROADCAST STATUS OF SCCP SUBSYSTEMS //
ZOBI:NA1;
ZOBL:NA1;
ZOBC:NA1,3D4B,FE::Y;
ZOBC:NA1,3FD1,FE::Y;
ZOBM:NA1,3D4B,FE::Y;
ZOBM:NA1,3FD1,FE::Y;
ZOBM:NA1,3D4B,FE:NA1,3FD1:Y;
ZOBI:NA1;
ZOBL:NA1;
!@Stop
## Step // CHANGE SCCP STATE //
ZNGI:NA1;
ZNGC:NA1,3D4B:ACT;
ZNGC:NA1,3FD1:ACT;
ZNGI:NA1;
!@Stop
## Step // CHANGE SUBSYSTEM STATE //
ZNHI:NA1;
ZNHC:NA1,3D4B:FE:ACT;
ZNHC:NA1,3FD1:FE:ACT;
ZNHI:NA1;
!@Stop
## Step // CREATE CGR //
ZRCI;
ZRCC:CGR=1,TYPE=CCS,NCGR=BSCSC28:DIR=IN,LSI=AINA1,NET=NA1,SPC=3FD1;
ZRCC:CGR=2,TYPE=CCS,NCGR=BSCSC28A:DIR=IN,LSI=AINA1,NET=NA1,SPC=3FD1;
!ZRCC:CGR=3,TYPE=CCS,NCGR=BSCSC28B:DIR=IN,LSI=AINA1,NET=NA1,SPC=3FD1;
ZRCI;
## !****************************************! ##
## Step // RESET BSC //
!ZUSS:SYM:C=DSK;
## Step // VERIFY CONFIGURATIONS //
## Step / VERIFY SIGNALLING BSC/MGW/MSS /
ZNET;
ZNEL;
ZNCI;
ZNLI;
ZNET:NA1;
ZNEO:NA1;
ZNES:NA1;
ZNER:NA1;
ZNRI:NA1;
ZNRT::NA1;
ZNSI:NA1;
ZNFJ:NA1;
ZNFI:NA1;
ZNVI:NA1;
ZNGI:NA1;
ZNHI:NA1;
ZNHJ:NA1;
ZNPI:NA1;
ZOBI:NA1;
ZOBL:NA1;
## !****************************************! ##

## Post-Re-homing Activities
2020-03-19
POST-RE-HOMING ACTIVITIES
Software Packages
Activity | Name
Delete | PRES13
Create | POSREHOM
Command Calendar Task
1
2
3
4
5
!*******************************************************!
!*** Post-Re-homing Activities - Alvaro R. Mendoza *****!
!*** Date: 2020-3-19 ***********************************!
!*******************************************************!
## !****************************************! ##
## Step // UNBLOCK COMMAND CALENDAR //
ZICL;
ZICB:1:UNBLOCK;
ZICB:2:UNBLOCK;
ZICB:3:UNBLOCK;
ZICB:4:UNBLOCK;
ZICB:5:UNBLOCK;
ZICL;
## Step // BACKUP //
## Step / DELETE OLD PACKAGE /
ZWQO:CR;
ZWQD:NAME=PRES13:DIRE,PRINTS;
ZWQO:CR;
## Step / CREATE FALLBACK /
ZWQO:CR;
ZWKS:NAME=POSREHOM,DIRE=POSREHOM,MODE=FULL;
ZWQO:CR;
## Step / PRINT PROGRESS OF FALLBACK /
ZWKI;
@Stop
## Step / CHECK THE STATUS OF FALLBACK (PHASES AND FILES WHERE HAS OCCURED ERROR) /
ZWKP:FULL:EMODE;
## Step / CHECK THE STATUS OF FALLBACK (ALL PHASES AND FILES) /
ZWKP:FULL:TOTAL;
## Step / VERIFY THE FALLBACK PACKAGE /
ZWQB:NAME=POSREHOM:FORM=FAILED,CW=ALL;
## Step // COPY NEWEST & VERIFIED FALLBACK TO FO //
## Step / VERIFY FREE SPACE ON MAGNETO-OPTICAL DISK /
ZIWX::F0,NODEF::%,%;
## Step / COPY THE BUILD FROM DISK TO MAGNETO-OPTICAL DISK /
ZIWY:S:DRIVE=WDU-B,PATH=/POSREHOM/;
ZIWY:D:DRIVE=FDU-N0,PATH=/,DRIVE=FDU-N0;
ZIBC:,,,,,,,,,DIR:DSN=POSREHOM;
## Step / VERIFY FREE SPACE ON MAGNETO-OPTICAL DISK /
ZIWX::F0,NODEF::%,%;
## !****************************************! ##